## Sprint 1
ITSC-3155 Software Engineering
Sprint 1 Backlog - Sample Window: Nov 17-23
Story Tasks / Endpoint / Commit | Story Point | Assigned to | Estimated Effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status | Sprint Review
US-01 Menu Management | 8 | Geonwoo Lee | 14 | 3 | 4 | 4 | 2 | 1 | 0 | Done | Accepted
Define validation for POST/PUT /sandwiches/ ¦ feat: validate sandwich data |  | Geonwoo Lee | 3 | 2 | 1 | 0 | 0 | 0 | 0 | Done | Validation accepted
Implement POST /sandwiches/ and GET /sandwiches/ ¦ feat: add sandwich create and read |  | Geonwoo Lee | 4 | 1 | 2 | 1 | 0 | 0 | 0 | Done | Create/read passed
Implement PUT/DELETE /sandwiches/{id} ¦ feat: complete sandwich CRUD |  | Geonwoo Lee | 4 | 0 | 1 | 2 | 1 | 0 | 0 | Done | Update/delete passed
Test sandwich CRUD endpoints ¦ test: add sandwich lifecycle test |  | Geonwoo Lee | 3 | 0 | 0 | 1 | 1 | 1 | 0 | Done | Test passed
US-02 Resource Inventory | 8 | Geonwoo Lee | 13 | 2 | 4 | 4 | 2 | 1 | 0 | Done | Accepted
Define validation for POST/PUT /resources/ ¦ feat: validate resource data |  | Geonwoo Lee | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done | Validation accepted
Implement POST/GET /resources/ ¦ feat: add resource create and read |  | Geonwoo Lee | 4 | 1 | 2 | 1 | 0 | 0 | 0 | Done | Create/read passed
Implement PUT/DELETE /resources/{id} ¦ feat: complete resource CRUD |  | Geonwoo Lee | 4 | 0 | 1 | 2 | 1 | 0 | 0 | Done | Update/delete passed
Test resource inventory endpoints ¦ test: verify resource persistence |  | Geonwoo Lee | 3 | 0 | 0 | 1 | 1 | 1 | 0 | Done | Test passed
US-03 Recipe Configuration | 5 | Geonwoo Lee | 13 | 0 | 2 | 4 | 4 | 2 | 1 | Done | Accepted
Define recipe relationships for POST/PUT /recipes/ ¦ feat: map recipe relationships |  | Geonwoo Lee | 2 | 0 | 1 | 1 | 0 | 0 | 0 | Done | Relationships accepted
Implement POST/GET /recipes/ ¦ feat: add recipe create and read |  | Geonwoo Lee | 4 | 0 | 1 | 2 | 1 | 0 | 0 | Done | Create/read passed
Implement PUT/DELETE /recipes/{id} ¦ feat: complete recipe CRUD |  | Geonwoo Lee | 4 | 0 | 0 | 1 | 2 | 1 | 0 | Done | Update/delete passed
Validate recipe foreign IDs ¦ test: cover recipe relationship errors |  | Geonwoo Lee | 3 | 0 | 0 | 0 | 1 | 1 | 1 | Done | Validation passed
SPRINT 1 TOTAL | 21 |  | 40 | 5 | 10 | 12 | 8 | 4 | 1 | Done | Sprint goal met

## Sprint 2
ITSC-3155 Software Engineering
Sprint 2 Backlog - Sample Window: Nov 24-30
Story Tasks / Endpoint / Commit | Story Point | Assigned to | Estimated Effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status | Sprint Review
US-04 Order Management | 13 | Geonwoo Lee | 20 | 3 | 5 | 6 | 4 | 1 | 1 | Done | Accepted
Implement POST/GET /orders/ ¦ feat: add order create and read |  | Geonwoo Lee | 5 | 2 | 2 | 1 | 0 | 0 | 0 | Done | Order create/read passed
Implement PUT/DELETE /orders/{id} ¦ feat: complete order CRUD |  | Geonwoo Lee | 5 | 1 | 2 | 2 | 0 | 0 | 0 | Done | Order CRUD passed
Implement POST/GET /order_details/ ¦ feat: add order item create and read |  | Geonwoo Lee | 5 | 0 | 1 | 2 | 2 | 0 | 0 | Done | Item create/read passed
Implement PUT/DELETE /order_details/{id} and tests ¦ test: verify order relationships |  | Geonwoo Lee | 5 | 0 | 0 | 1 | 2 | 1 | 1 | Done | Relationship test passed
US-05 Checkout and API Quality | 13 | Geonwoo Lee | 22 | 1 | 3 | 5 | 6 | 5 | 2 | Done | Accepted
Implement GET /orders/{id}/summary ¦ feat: calculate order totals |  | Geonwoo Lee | 4 | 1 | 1 | 1 | 1 | 0 | 0 | Done | Summary accepted
Implement POST /orders/{id}/checkout ¦ feat: add inventory-aware checkout |  | Geonwoo Lee | 8 | 0 | 2 | 3 | 2 | 1 | 0 | Done | Checkout accepted
Test 409 errors, resource deduction, and repeat checkout ¦ test: cover checkout workflow |  | Geonwoo Lee | 6 | 0 | 0 | 1 | 2 | 2 | 1 | Done | Three tests passed
Add GET /, GET /health, Swagger metadata, and README ¦ docs: finalize sample API |  | Geonwoo Lee | 4 | 0 | 0 | 0 | 1 | 2 | 1 | Done | Documentation accepted
SPRINT 2 TOTAL | 26 |  | 42 | 4 | 8 | 11 | 10 | 6 | 3 | Done | Sprint goal met